## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 2750
|  | Actual: | 3751.25
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 1 | Developer | Other (Describe) |  | 2026-02-07 10:00 | 2026-02-08 20:00 | Completed | 3 | 4 | 75 | 100 | Descargar la workspace e instanciar el starter project "Hello-World" como Acme-Starters-C
2 | T0002/M | Management | Student 1 | Manager | Initialise repository |  | 2026-02-09 10:00 | 2026-02-09 12:00 | Completed | 1 | 2 | 50 | 100
3 | T0003/M | Management | Student 1 | Manager | Supervise task |  | 2026-02-08 11:00 | 2026-02-24 13:00 | Completed | 1.5 | 3 | 75 | 150
4 | T0004/D | Development | Student 1 | Developer | Customise the starter |  | 2026-02-08 14:00 | 2026-03-20 18:00 | Completed | 2 | 4 | 50 | 100
5 | T0005/D | Development | Student 2 | Developer | Customise the starter |  | 2026-02-08 14:00 | 2026-03-20 18:00 | Completed | 2 | 4 | 50 | 100
6 | T0006/D | Development | Student 3 | Developer | Customise the starter
7 | T0007/D | Development | Student 4 | Developer | Customise the starter |  | 2026-02-15 10:10 | 2026-02-15 11:40 | Completed | 2.5 | 1.5 | 62.5 | 37.5 | Customizar el changelog.txt, license.txt y el favicon
8 | T0008/D | Development | Student 5 | Developer | Customise the starter
9 |  |  | Student 5 | Developer | Write report
10 | T0010/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-12 17:40 | 2026-02-12 19:30 | Completed | 1.8 | 1.8 | 0 | 0
11 | T0011/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-19 17:40 | 2026-02-19 19:30 | Completed
12 | T0012/O | Other | Student 1 | Student | Attend lecture |  | 2026-01-26 15:30 | 2026-01-26 17:20 | Completed | 1.833 | 1.833 | 0 | 0
13 | T0013/O | Other | Student 1 | Student | Attend lecture |  | 2026-01-29 17:40 | 2026-01-29 19:30 | Completed | 1.833 | 1.833 | 0 | 0
14 | T0014/O | Other | Student 1 | Student | Attend lecture |  | 2020-02-02 15:30 | 2026-02-02 17:20 | Completed | 1.833 | 1.833 | 0 | 0
15 | T0015/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-05 17:40 | 2026-02-05 19:30 | Completed | 1.833 | 1.833 | 0 | 0
16 | T0016/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-09 15:30 | 2026-02-09 17:20 | Completed | 1.833 | 1.833 | 0 | 0
17 | T0017/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-12 17:40 | 2026-02-12 19:30 | Completed | 1.833 | 1.833 | 0 | 0
18 | T0018/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-16 15:30 | 2026-02-16 17:20 | Completed | 1.833 | 1.833 | 0 | 0
19 | T0019/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-19 17:40 | 2026-02-19 19:30 | Completed | 1.833 | 1.833 | 0 | 0
20 | T0020/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-23 15:30 | 2026-02-23 17:20 | Completed | 1.833 | 1.833 | 0 | 0
21 | T0021/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-26 17:40 | 2026-02-26 19:30 | Completed
22 | T0022/D | Development | Student 4 | Developer | Other (Describe) |  | 2026-02-28 14:00 | 2026-02-28 14:15 | Completed | 0.3 | 0.3 | 7.5 | 7.5 | Crear cuentas de administrador1 y administrador2
23 | T0023/D | Development | Student 4 | Developer | Other (Describe) |  | 2026-02-28 14:21 | 2026-02-28 14:59 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Implementar TickerValidator
24 | T0024/D | Development | Student 4 | Developer | Other (Describe) |  | 2026-02-28 15:13 | 2026-02-28 19:27 | Completed | 3 | 4 | 75 | 100 | Implementar modelo de datos Student4
25 | T0025/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-14 17:30 |  | Completed |  |  |  |  | Implementar modelo de datos Student5
26 | T0026/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-23 12:00 | 2026-02-23 14:00 | Completed |  |  |  |  | Implementar la restricción ValidHeader
27 | T0027/O | Other | Student 1 | Student | Attend lecture |  | 2026-02-26 17:40 | 2026-02-26 19:30 | Completed | 1.833 | 1.833 | 0 | 0
28 | T0028/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-02-13 20:00 | 2026-03-10 11:00 | Completed | 3 | 10 | 75 | 250 | Implementar modelo de datos Student1
29 | T0029/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-02-22 17:00 | 2026-02-26 17:00 | Completed | 0.5 | 1 | 12.5 | 25 | Implementar la restricción ValidText
30 | T0030/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-01 17:00 |  |  | 2 |  | 50 |  | Implementar modelo de datos Student3
31 | T0031/D | Development | Student 3 | Developer | Other (Describe) | T0030/D | 2026-03-02 10:00 |  |  | 2 |  | 50 |  | Ejemplo de datos positivos
32 | T0032/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-02 12:36 | 2026-03-14 22:03 | Completed | 2 | 2.5 | 50 | 62.5 | Ejemplo de datos negativos
33 | T0033/O | Other | Student 1 | Student | Attend lecture |  | 2026-03-02 15:30 | 2026-03-02 17:40 | Completed | 1.833 | 2 | 0 | 0
34 | T0034/D | Development | Student 1 | Developer | Other (Describe) | T0027/O | 2026-02-27 20:00 | 2026-03-13 20:00 | Completed | 2 | 6 | 50 | 150 | Ejemplo de datos positivos
35 | T0035/D | Development | Student 1 | Developer | Other (Describe) | T0027/O | 2026-02-27 20:00 | 2026-03-13 20:00 | Completed | 2 | 3.5 | 50 | 87.5 | Ejemplo de datos negativos
36 | T0036/M | Management | Student 1 | Manager | Other (Describe) |  | 2026-03-07 14:00 | 2026-03-07 15:40 | Completed | 1 | 1.7 | 50 | 85 | Estudiar, actualizar y subir la version 3 (REV3) del Workspace
37 | T0037/O | Other | Student 1 | Student | Attend lecture |  | 2026-03-05 17:40 | 2026-03-05 19:30 | Completed | 1.833 | 2 | 0 | 0
38 | T0038/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-08 17:40 | 2026-03-14 22:03 | Completed | 2 |  | 50 |  | Añadir feature visual strategies
39 | T0039/D | Development | Student 3 | Developer | Customise the starter |  | 2026-03-09 02:40 |  |  | 0.2 | 0.2 | 5 | 5 | Cambiar mensaje ventana buscador
40 | T0040/D | Development | Student 1 | Developer | Implement feature | T0027/O | 2026-03-08 21:00 | 2026-03-15 17:00 | Completed | 4 | 6 | 100 | 150 | Añadir feature S1/2
41 | T0041/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-09 10:00 | 2026-03-09 12:30 | Completed |  |  |  |  | Añadir datos de sampleo Student5
42 | T0042/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-09 12:00 |  | Ongoing |  |  |  |  | Añadiir feature S5/2
43 | T0043/O | Other | Student 1 | Student | Attend lecture |  | 2026-03-09 15:30 | 2026-03-09 15:30 | Completed | 1.833 | 1.83 | 0 | 0
44 | T0044/O | Other | Student 1 | Student | Attend lecture |  | 2026-03-12 17:40 | 2026-03-12 19:30 | Completed | 1.833 | 1.83 | 0 | 0
45 | T0045/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-14 18:30 | 2026-03-14 20:10 | Completed | 1 | 1.6 | 25 | 40 | Arreglar feaure S4/2
46 | T0046/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-01 11:30 | 2026-03-15 09:00 | Completed | 10 | 15 | 250 | 375 | Implementar modelos completos con datos de prueba
47 | T0047/D
48 | T0048/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-14 20:11 | 2026-03-14 22:03 | Completed | 2 | 2 | 50 | 50 | Implementar feature S4/3
49 | T0049/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-15 11:18 | 2026-03-15 21:20 | Completed | 6 | 10 | 150 | 250 | Implementar feature S4/4
50 | T0050/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-15 09:00 | 2026-03-17 10:30 | Completed | 5 | 5 | 125 | 125 | Implementar feature S2/2 y datos de prueba erroneos
51
52
53 | T0053/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-15 12:00 | 2026-03-18 12:00 | Completed | 2 | 3 | 50 | 75 | Implementar feature S1/3
54 | T0054/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-15 15:00 | 2026-03-20 12:00 | Completed | 10 | 15 | 250 | 375 | Implementar feature S1/4
55 | T0055/D | Development | Student 3 | Developer | Implement feature | T0038/D | 2026-03-16 15:00 |  |  | 3 |  | 75 |  | Implementar feature S3
56 | T0056/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-15 19:30 | 2026-03-15 22:45 | Completed | 3 | 3.15 | 75 | 78.75 | Implementar feature S5/3
57 | T0057/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-15 22:45 | 2026-03-16 13:30 | Completed | 5 | 9 | 125 | 225 | Implementar feature S5/4
58 | T0058/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-16 12:30 | 2026-03-16 13:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Arreglar sampleo S5
59 | T0059/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-17 10:06 | 2026-03-17 14:23 | Completed | 3 | 4 | 75 | 100 | Arreglar feature S4/4
60 | T0060/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-17 10:30 | 2026-03-17 22:30 | Completed | 10 | 9 | 250 | 225 | Implementar feature S2/3 y S2/4
61 | T0061/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-20 | 2026-03-20 03:12 | Completed | 2 | 3 | 50 | 75 | Mas arreglos de las features de S4
62 | T0062/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-20 00:30 | 2026-03-20 02:12 | Completed | 1 | 1.3 | 25 | 32.5 | Administrator y añadir campaigns a any
63 | T0063/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-18 10:30 | 2026-03-19 10:30 | Completed | 3 | 4 | 75 | 100 | Arreglar features
64 | T0064/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-20 09:00 | 2026-03-20 12:00 | Completed | 3 | 3 | 75 | 75 | Ultimos ajustes S5 e internacionalización
65 | T0065/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-20 12:30 | 2026-03-20 13:12 | Completed | 0.5 | 0.6 | 12.5 | 15 | Fix i18n
66 | T0066/O | Other | Student 4 | Student | Attend lecture |  | 2026-01-26 15:30 | 2026-01-26 17:20 | Completed
67 | T0067/O | Other | Student 4 | Student | Attend lecture |  | 2026-01-29 17:40 | 2026-01-29 19:30 | Completed
68 | T0068/O | Other | Student 4 | Student | Attend lecture |  | 2020-02-02 15:30 | 2026-02-02 17:20 | Completed
69 | T0069/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-05 17:40 | 2026-02-05 19:30 | Completed
70 | T0070/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-09 15:30 | 2026-02-09 17:20 | Completed
72 | T0072/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-16 15:30 | 2026-02-16 17:20 | Completed
74 | T0074/O | Other | Student 4 | Student | Attend lecture |  | 2026-02-23 15:30 | 2026-02-23 17:20 | Completed
75
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O